## Sheet1
Change Control Log
Change ID | Date Submitted | Submitted By | Description | Reason | Impact Analysis | Priority | Approval Status | Approved By & Date
1 | 2026-07-01 | Exam Department | Forget Password feature | student use forgrt passowrd feature | core feature , database use , login UI , I day extra for devlopment phase | High | Approved | Project Manager 2-july-2026
2 | 2026-07-03 | exam Department | Add SMS notification for confirmation of exam registration | Students need instant confirmation after registration. | implement SMS module , Add 2 days to develope the phase | High | Approved | Project Manager 4-july-2026
3 | 2026-07-05 | Finance Department | Add online payment receipt download | Students need proof of fee payment anytime. | Changes payment module and add download option and add 2 more days for development | High | Approved | Project Manager 7-july-2027
4 | 2026-07-08 | Exam Department | Add result rechecking request feature | Students should be able to apply for rechecking online. | Adds new forms and required 3 more days for it | Medium | Approved | Project Manager 10-july-2028
5 | 2026-07-11 | Academic Department | Add email notification when results are published | Students want notification whan result is uploaded to see the result fast | Integrates email notification service.Add 4 days for this feature to implement | Medium | Approved | Project Manager 15-july-2029